## Tasks
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start date | Due date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Description
-ahmj-PwgEWUxysah86su8kAAh4q | Save Question, Answer, and Relevance | To do | Completed | Medium | Ediriweera E R L C it21822230 | Ediriweera E R L C it21822230 | 08/19/2025 |  |  | false | false | 09/26/2025 | Ediriweera E R L C it21822230 |  |  |  | The UI should be a carousel
1XMKhVacX0CD4ntMpIaFl8kAKkqe | creates models for Voice and emotions | To do | Completed | Medium | Abeywardana B.A.I.S it21294334 | Fernando N.D.R.N it21359606 | 09/26/2025 |  |  | false | false | 09/26/2025 | Fernando N.D.R.N it21359606
3PhsVk2yVU6_IX6LCvZ6VckAFMX3 | Report Editing | To do | Completed | Medium | Ediriweera E R L C it21822230;Karunarathna K.A.D it21813252;Fernando N.D.R.N it21359606 | Ediriweera E R L C it21822230 | 08/06/2025 |  |  | false | false | 08/10/2025 | Ediriweera E R L C it21822230
3pW0wsXF2ky0dvLjNYqqT8kADmEp | Implement google authentication for Signup page | To do | Completed | Medium | Karunarathna K.A.D it21813252 | Ediriweera E R L C it21822230 | 08/12/2025 |  |  | false | false | 08/15/2025 | Karunarathna K.A.D it21813252
4FGrJXmCPEW4XWJn8V7J0ckAOpMn | Create Investigation PopUp | To do | Completed | Medium | Karunarathna K.A.D it21813252 | Ediriweera E R L C it21822230 | 08/12/2025 | 08/12/2025 | 08/12/2025 | false | false | 08/12/2025 | Karunarathna K.A.D it21813252
6EjnNQtY6EmlYJpkvtxl_8kAPkpT | Navigation Bar | To do | Completed | Medium | Karunarathna K.A.D it21813252 | Ediriweera E R L C it21822230 | 08/10/2025 |  |  | false | false | 08/11/2025 | Karunarathna K.A.D it21813252 |  |  |  | Home Search Files Investigation Analytics. Resources Learn Registration
6IUI7WTvTEGMnp0ZBmrro8kAPu8J | Analytics Dashboard Creation | To do | Not started | Medium | Ediriweera E R L C it21822230 | Ediriweera E R L C it21822230 | 08/12/2025 |  |  | false | false
7SaP11gavUeTZdsyBBtQDskAAC08 | Investigation Data table | To do | Not started | Urgent | Abeywardana B.A.I.S it21294334 | Ediriweera E R L C it21822230 | 08/14/2025 |  |  | false | false
9lkk7GWgtECUoAmmijatqMkAJO7a | Create Investigation Popup NIC number field - change from dropdown to manual input field | To do | Completed | Medium | Abeywardana B.A.I.S it21294334 | Ediriweera E R L C it21822230 | 08/19/2025 |  |  | false | false | 09/26/2025 | Fernando N.D.R.N it21359606
C_8rFC79QUWUJb-qB5-mO8kAGw_N | User Dashboard - Learning Paths Suggestions | To do | Completed | Medium | Karunarathna K.A.D it21813252 | Ediriweera E R L C it21822230 | 08/12/2025 |  |  | false | false | 09/26/2025 | Karunarathna K.A.D it21813252
CfyPB_scj02DyMhcl5JRgskAB15s | Next & Google Auth Integration | To do | Not started | Urgent | Abeywardana B.A.I.S it21294334 | Ediriweera E R L C it21822230 | 08/14/2025 |  |  | false | false
ED6bdVeuS0K6hfW1KIKwMskAPIG- | Admin privileges for sign-up | To do | Not started | Medium | Fernando N.D.R.N it21359606;Abeywardana B.A.I.S it21294334 | Ediriweera E R L C it21822230 | 08/15/2025 |  |  | false | false | [5 empty] | Give 1 user admin privileges to verify new users to the system based on Police ID number. (similar to Active Directory)
Ec8Nw80C5kWr3Q3JJKDDr8kAOCFb | Video of working system. | To do | Completed | Medium | Ediriweera E R L C it21822230;Karunarathna K.A.D it21813252;Abeywardana B.A.I.S it21294334;Fernando N.D.R.N it21359606 | Ediriweera E R L C it21822230 | 08/06/2025 |  |  | false | false | 09/26/2025 | Fernando N.D.R.N it21359606
H56TN99fD0qimUGkZcTrPskACbyb | Case Numbers of Reports | To do | Not started | Medium |  | Ediriweera E R L C it21822230 | 08/10/2025 |  |  | false | false
IGeoKk3PG064CKE5NwbiNskAId9F | Make Admin Panel | To do | Completed | Medium | Fernando N.D.R.N it21359606 | Ediriweera E R L C it21822230 | 08/06/2025 |  |  | false | false | 09/17/2025 | Fernando N.D.R.N it21359606
M_hsme_vPUyPMOOFxzViOskAOzJR | Need to Use Table Joins when retrieving data | To do | Completed | Medium | Ediriweera E R L C it21822230;Fernando N.D.R.N it21359606 | Ediriweera E R L C it21822230 | 08/08/2025 |  |  | false | false | 09/26/2025 | Fernando N.D.R.N it21359606
MdRJ6b2gEEanFNa_pQoY78kAMBjA | user profile page | To do | Completed | Medium | Ediriweera E R L C it21822230;Karunarathna K.A.D it21813252 | Ediriweera E R L C it21822230 | 08/07/2025 |  |  | false | false | 09/26/2025 | Karunarathna K.A.D it21813252 |  |  |  | Investigator profile
MsOBkO4PFkuvfB9lGyQDnMkAHszj | Validation and auto-load based on NIC and Name | To do | Completed | Medium | Fernando N.D.R.N it21359606 | Ediriweera E R L C it21822230 | 08/12/2025 |  |  | false | false | 08/21/2025 | Fernando N.D.R.N it21359606
PkhBiMfQ7UOrzCXYdUyatMkANPYt | Session controls - move to a single line on header | To do | Completed | Medium | Ediriweera E R L C it21822230 | Ediriweera E R L C it21822230 | 08/14/2025 |  |  | false | false | 09/26/2025 | Ediriweera E R L C it21822230
PuXV8DhweU2Icj9b80nVGMkAFEFa | User Dashboard - Change popular to show video | To do | Completed | Medium | Karunarathna K.A.D it21813252 | Ediriweera E R L C it21822230 | 08/12/2025 |  |  | false | false | 09/26/2025 | Karunarathna K.A.D it21813252
QssquSw6D0mKm6N6qdncg8kANuId | Analytics - Crime Statistics and Prediction Page | To do | Completed | Medium | Fernando N.D.R.N it21359606 | Ediriweera E R L C it21822230 | 08/12/2025 |  |  | false | false | 08/21/2025 | Fernando N.D.R.N it21359606
TuW8JbLKm0eHh2rcQ8zWjckAHNlV | Report Details Card - make collapsible | To do | Completed | Medium | Ediriweera E R L C it21822230 | Ediriweera E R L C it21822230 | 08/14/2025 |  |  | false | false | 09/26/2025 | Ediriweera E R L C it21822230
UBTrxSuctE-bOnfMfRqaiskAKIuM | Person Registration | To do | Completed | Medium | Karunarathna K.A.D it21813252 | Ediriweera E R L C it21822230 | 08/08/2025 | 08/12/2025 | 08/12/2025 | false | false | 08/12/2025 | Karunarathna K.A.D it21813252 |  |  |  | implement a method to retrieve reports when user provide the NIC number
UY-H0ytMNEeQxsEd9F0taMkALFLi | Opinion - Confirm with police about the details in db | To do | Completed | Medium | Ediriweera E R L C it21822230 | Ediriweera E R L C it21822230 | 08/12/2025 |  |  | false | false | 09/26/2025 | Ediriweera E R L C it21822230
XJ4-i-gfoE6GG41fsbAbsckAOnyo | Bug - don't show processing data | To do | Completed | Medium | Karunarathna K.A.D it21813252 | Ediriweera E R L C it21822230 | 08/12/2025 |  |  | false | false | 08/12/2025 | Karunarathna K.A.D it21813252 |  |  |  | Enough to extract to session dashboard when "create investigation button" is pressed no need to show on pop up.
YorD9mBly0-bZV9bz2X6nskAK_jf | Convert Unique ID to fit common naming convention and form validation | To do | Completed | Medium | Ediriweera E R L C it21822230;Karunarathna K.A.D it21813252 | Ediriweera E R L C it21822230 | 08/12/2025 |  |  | false | false | 08/12/2025 | Karunarathna K.A.D it21813252
YyZTOvoJtU26fUwMGL0prMkAFSPS | Sinhala Language | To do | Completed | Medium | Ediriweera E R L C it21822230 | Ediriweera E R L C it21822230 | 08/08/2025 |  |  | false | false | 09/26/2025 | Ediriweera E R L C it21822230
_5RA2QlPiU2Zbc8aeT1D0MkAN6J3 | Implement Google Authentication in Login form | To do | Completed | Medium | Karunarathna K.A.D it21813252 | Ediriweera E R L C it21822230 | 08/12/2025 |  |  | false | false | 08/15/2025 | Karunarathna K.A.D it21813252
aCb61EGfFUy5LNs4d6ArUMkAFFgV | connect login and sign-in | To do | Not started | Medium | Abeywardana B.A.I.S it21294334 | Ediriweera E R L C it21822230 | 08/07/2025 |  |  | false | false
fv5jPXnu2Eei1N0oabPHTskAMRlK | Session Dashboard | To do | Completed | Medium | Ediriweera E R L C it21822230 | Ediriweera E R L C it21822230 | 08/10/2025 |  |  | false | false | 09/26/2025 | Ediriweera E R L C it21822230
hW8LRG0QekCwuOwRr5V6L8kAGdnc | Investigation Table | To do | Completed | Medium | Fernando N.D.R.N it21359606 | Ediriweera E R L C it21822230 | 08/12/2025 | 08/12/2025 | 08/12/2025 | false | false | 08/21/2025 | Fernando N.D.R.N it21359606
hpnom-JGG02CmXjNnw7QiskAEGjn | Report Download function of file uploads | To do | Completed | Medium | Karunarathna K.A.D it21813252 | Ediriweera E R L C it21822230 | 08/14/2025 |  |  | false | false | 08/15/2025 | Karunarathna K.A.D it21813252
ht6j1e1kNU69SYeNFIbV3ckAOEuv | Change Question Generation Prompts to use persontype | To do | Completed | Medium | Ediriweera E R L C it21822230 | Ediriweera E R L C it21822230 | 08/19/2025 |  |  | false | false | 09/26/2025 | Ediriweera E R L C it21822230
inCPZKQjDEqve0hyxhKNQckALz1Q | Make System Flow | To do | Completed | Urgent | Ediriweera E R L C it21822230;Karunarathna K.A.D it21813252;Fernando N.D.R.N it21359606;Abeywardana B.A.I.S it21294334 | Ediriweera E R L C it21822230 | 08/06/2025 |  |  | false | false | 09/26/2025 | Fernando N.D.R.N it21359606 |  |  |  | Pop Up
k2xez3Grd0a7Mo0_iHk4JckAJKS2 | Bug - New Investigation cancel Button not working | To do | Completed | Medium | Karunarathna K.A.D it21813252 | Ediriweera E R L C it21822230 | 08/12/2025 |  |  | false | false | 08/12/2025 | Karunarathna K.A.D it21813252
lgSUxObfLEmQ7S1cvU7ozckALoKM | People Registry | To do | Completed | Medium | Ediriweera E R L C it21822230;Karunarathna K.A.D it21813252 | Ediriweera E R L C it21822230 | 08/12/2025 |  |  | false | false | 08/19/2025 | Karunarathna K.A.D it21813252
oyOPH9ETz0aA2neN2tzi38kAI5ke | Create Model | To do | Completed | Medium | Fernando N.D.R.N it21359606 | Ediriweera E R L C it21822230 | 09/17/2025 |  | 08/15/2025 | false | false | 09/17/2025 | Fernando N.D.R.N it21359606
qMIwRVlZTkWz5FWg0-ymKMkAC4fv | Retry Mechanism to use chatgpt when gemini is not working | To do | Not started | Medium | Ediriweera E R L C it21822230 | Ediriweera E R L C it21822230 | 08/06/2025 |  |  | false | false
qNn71CWeCkuhFonjDBtr7MkAJ1b8 | Analytics - Predictions Page | To do | Completed | Medium | Karunarathna K.A.D it21813252 | Ediriweera E R L C it21822230 | 08/12/2025 |  |  | false | false | 08/13/2025 | Karunarathna K.A.D it21813252
rkyJuijD4Eik8OZU-JbbVckAAZlo | Person Details View | To do | Completed | Medium | Ediriweera E R L C it21822230;Karunarathna K.A.D it21813252 | Ediriweera E R L C it21822230 | 08/12/2025 |  |  | false | false | 08/12/2025 | Karunarathna K.A.D it21813252
uE5gD2miVkmMCK4r-ilGe8kAH4de | generate sample police b reports with the new existing b reports for model training | To do | Completed | Medium | Fernando N.D.R.N it21359606 | Ediriweera E R L C it21822230 | 08/07/2025 |  |  | false | false | 08/21/2025 | Fernando N.D.R.N it21359606
vV0xpUo_pESV2Ex_sUfp38kAMK2m | have to test the system | To do | Completed | Medium | Fernando N.D.R.N it21359606 | Fernando N.D.R.N it21359606 | 09/26/2025 |  |  | false | false | 09/26/2025 | Fernando N.D.R.N it21359606
yXfEv5DhCESWhjBS58DdIMkAJWh5 | Validation for NIC : if age is less than 16 mark as minor | To do | Completed | Medium | Karunarathna K.A.D it21813252 | Ediriweera E R L C it21822230 | 08/20/2025 |  |  | false | false | 08/22/2025 | Karunarathna K.A.D it21813252
z_I2GgQ1YEeAt3Bznll2m8kAPY3N | Final Reports | To do | Not started | Medium | Ediriweera E R L C it21822230 | Ediriweera E R L C it21822230 | 08/12/2025 | 08/12/2025 | 08/27/2025 | false | true

## Plan name
Plan name | RESEARCH
Plan ID | VwsCcR6tt0iUpRnpQg60HMkADY2i
Date of export | 09/26/2025